## Slide 1
NEW AIYANSH INTERPRETIVE CENTRE
Strategic Communications Plan
A working presentation for aligning audiences, story, tools and website development
Prepared for discussion | May 2026
Greenhill Communications
01
Notes: Open by framing this as a working deck, not a final strategy imposed from outside. The goal is to help the group see how their existing answers already contain the foundations of a communications plan: audiences, story, tools, website structure, and implementation priorities.

## Slide 2
WORKING SESSION
Purpose of the meeting
The practical task: move from good intentions and scattered tools to a coherent communications platform.
1. Confirm direction
Clarify what communications must accomplish for the Centre and the Village Government.
2. Prioritize audiences
Turn broad audience groups into concrete user journeys and visitor needs.
3. Define the website
Identify the core pages, functions, content and governance required for launch.
4. Agree next steps
Leave with a practical phased plan, roles and immediate decisions.
Outcome: a shared framework for a strategic communications plan and website development roadmap.
Source: Website Development Questions, May 7, 2026.
02
Notes: Use this slide to set expectations. The meeting does not need to solve every content question. It should align around the purpose of the communications system, the audiences, the story, and the immediate work required to build an effective website and related tools.

## Slide 3
STARTING POINT
What we heard in the Q&A
Current communications instruments
Digital: word of mouth, social media, radio / public service messaging.
Analogue: brochure / flyer, signage, front façade, CFNR radio PSA.
Immediate communications priority
Make sure people know the New Aiyansh Interpretive Centre exists, is open, and can be contacted easily.
Use technology professionally and in alignment with Village Government guidelines.
Strategic implication
The Centre needs more than a website. It needs a connected communications system with clear ownership, repeatable content, contact pathways and measurement.
The existing tools are useful, but they need to be connected, amplified and governed.
Source: Website Development Questions, May 7, 2026.
03
Notes: Ground the discussion in what the group already said: they have channels, but not yet a strategic infrastructure. The key move is to connect word of mouth, social, radio, print and visitor-facing tools through the website.

## Slide 4
FROM VISIBILITY GAP TO INFRASTRUCTURE
The strategic diagnosis
A communications plan should solve three related problems:
1
Visibility
People need to know NAIC exists, where it is, when it is open, and why it matters.
2
Coherence
Visitors, youth, community members and partners should all encounter the same core story.
3
Continuity
Communications should continue after launch through events, updates, email, social and analytics.
The website is the anchor - but the plan must also define the tools, rhythms and responsibilities around it.
Source: Website Development Questions, May 7, 2026.
04
Notes: This is the central strategic argument. A website alone will not solve the communications problem unless it is connected to a plan for audiences, content, technology, staff workflow and metrics.

## Slide 5
WHAT SUCCESS SHOULD LOOK LIKE
Communications goals
Awareness
Tourists and regional visitors know the Centre exists and understand why it is worth visiting.
Access
People can quickly find location, hours, contact information, events and ways to ask questions.
Understanding
Visitors leave with a clearer sense of Nisga’a identity, New Aiyansh history, language, culture and community.
Engagement
Youth, community members, other Nisga’a communities and urban locals see the Centre as a living resource, not only a visitor stop.
Working statement: NAIC communications should make the Centre visible, accessible, understandable and actively connected to community life.
Source: Website Development Questions, May 7, 2026.
05
Notes: Invite the group to test these goals. Ask: Do these four goals describe what communications must accomplish? Is anything missing, especially around protocol, language, education, visitor services, or Village Government alignment?

## Slide 6
WHO THE PLAN MUST SERVE
Audience architecture
The Q&A identifies several audiences. The plan should organize them by need, not only by category.
NAIC
story
Primary
Secondary
Community
Institutional
Tourists
worldwide
Activity visitors:
fishing, hiking,
camping
Nisga’a youth,
students, community
members
GVG staff,
stimulus workers,
Nisga’a communities
and Urban Locals
Audience planning question: What does each group need to know, feel and do after encountering NAIC communications?
Source: Website Development Questions, May 7, 2026.
06
Notes: This slide helps avoid the common mistake of treating “the public” as one audience. A tourist needs practical visit information. A youth audience needs belonging, identity and access to community history. A government/staff audience needs approved, consistent information and workflow.

## Slide 7
PLANNING MATRIX
Audience needs and desired actions
Audience
Need / question
Desired action
Tourists
Where is it? Is it open? Why should I visit?
Plan a visit; contact the Centre; share the experience.
Activity visitors
What can I do in the area, and how does NAIC orient me to place?
Use NAIC as a cultural and visitor information gateway.
Nisga’a youth / students
Where do I come from? How does this history connect to family, language and lineage?
Engage with exhibits, learning resources and events.
Community members
How does this Centre reflect our story and contemporary life?
Contribute knowledge, photos, events and feedback.
Nisga’a communities / Urban Locals
How can we connect to the Centre from elsewhere?
Stay informed, attend events, share resources.
Use this matrix to check every website page, brochure, radio spot and social post against a real audience need.
Source: Website Development Questions, May 7, 2026.
07
Notes: This matrix can become a practical planning tool. It translates audience categories into questions that communications must answer. Ask the group if these needs are accurate and what should be added, especially around protocols and sensitive cultural materials.

## Slide 8
WHAT NAIC NEEDS TO COMMUNICATE
Story and message platform
Core story: how we came to live in New Aiyansh - including language, culture, history, family lineage, and the continuing life of the community.
Place
Where NAIC is located and how New Aiyansh sits within the Nisga’a Nation.
History
The story going back to the 1800s and from Time Before Memory.
Culture + language
A living story of knowledge, sacredness, family, language and continuity.
Contemporary life
The Centre as a present-day community, learning and visitor resource.
Message discipline: every tool should reinforce the same core story while adapting to each audience.
Source: Website Development Questions, May 7, 2026.
08
Notes: The Q&A already gives a strong core story. The communications task is to turn that story into an agreed message platform that can guide website copy, social captions, print materials, radio messaging, signage, and conversations with visitors.

## Slide 9
BRAND DIRECTION
Look, feel and cultural tone
Knowledgeable
Clear, accurate, well-organized information.
Historical
Archival photos, timelines, place-based context.
Sacred
Respectful treatment of culture, language and protocols.
Contemporary
Present-day community, technology and living relationships.
Design implication: the website should combine archival depth with a clean contemporary interface - not a museum brochure recreated online.
Important governance note: cultural materials, language use and archival images need clear approval protocols.
Source: Website Development Questions, May 7, 2026.
09
Notes: This is where visual design and cultural governance meet. Ask about existing logos, colour rules, Village Government guidelines, image rights, language protocols, archival permissions, and what should or should not be public online.

## Slide 10
TOOL STRATEGY
The website as communications hub
The website should become the trusted centre of the system. Other tools should point people back to it.
Website
source of truth
Social media
Radio / PSA
Brochure + signage
Email newsletter
Events
Analytics
Practical rule: publish once on the website, then repurpose into email, social, print, signage and radio.
Source: Website Development Questions, May 7, 2026.
10
Notes: This slide explains why the website is not simply another communication channel. It is the place where official, approved, current information lives. Every other tool can be shorter, faster and more flexible because it points back to the website.

## Slide 11
INFORMATION ARCHITECTURE
Proposed website architecture
A simple structure should help first-time visitors, returning visitors and community audiences find what they need quickly.
Home
Clear welcome, visitor actions, current hours, featured story.
Visit the Centre
Hours, location, contact, maps, accessibility, visitor FAQs.
Our Story
Who, what, where and why; New Aiyansh past and present.
Exhibits + Archives
Storyline, archival photos, present-day photos, videos and kiosks.
Community + Youth
Learning resources, school connections, community contribution pathways.
Events + Updates
Community events, announcements, visitor programming.
Contact
Names, phone, email, feedback, media and partnership inquiries.
Navigation should mirror the audience journey: discover -> understand -> visit -> connect.
The structure can incorporate existing categories: mission, profile, communities, treaty, events and contacts.
Source: Website Development Questions, May 7, 2026.
11
Notes: This is a suggested architecture. The meeting should confirm whether any sections need different names, which cultural content needs approval, and whether treaty-related content should be a distinct section or integrated into the story section.

## Slide 12
WHAT THE SITE SHOULD DO
Essential website functionality
Find us quickly
Prominent hours, location, phone, email, maps and contact buttons.
Tell the story
Storyline pages supported by archival photos, present-day images, video and approved language.
Promote events
Simple event/update system that can feed social and email communications.
Build a list
Newsletter signup connected to a secure contact database.
Invite feedback
A moderated contact / suggestion form for corrections, questions and improvements.
Measure reach
Analytics dashboard for visits, referrals, search terms and high-value pages.
Build only what can be maintained: practical functionality, clear ownership and staff-friendly editing.
Source: Website Development Questions, May 7, 2026.
12
Notes: The Q&A answer to functionality is not fully detailed, so this slide proposes a minimum useful set. Emphasize that the site should be manageable by staff and not become dependent on complex custom features unless they are truly needed.

## Slide 13
WEBSITE PLUS REPEATABLE TOOLS
Communications tools ecosystem
The Centre’s communications should work as a small, practical system:
Website
Official source of truth and archive.
E-newsletter
Updates to tourists, community, schools, partners and Nisga’a Urban Locals.
Social templates
Short posts that point back to website pages and events.
Print + QR
Brochures, flyers and signage with QR codes to live information.
Radio / PSA kit
Approved short scripts for CFNR and public-service announcements.
Content calendar
A shared schedule for seasonal visitor information, events and story features.
The goal is not more work; it is one approved message used across several channels.
Priority: website first, then email list and content calendar, then templates for repeatable outreach.
Source: Website Development Questions, May 7, 2026.
13
Notes: This slide is useful for a group that may think of communications tools separately. Explain the workflow: a new event or story is posted once on the website; a newsletter excerpt goes out; social posts point back; a radio note or print flyer uses the same approved wording.

## Slide 14
A LIVING SITE, NOT A ONE-TIME BUILD
Content strategy
Visitor essentials
Hours, location, seasonal information, contact and visitor FAQs.
Story features
Short, approved pieces on language, history, community, archival images and exhibits.
Events + programs
Community events, school visits, learning opportunities and visitor programming.
Community contributions
Pathways for photos, corrections, memories, questions and feedback.
Create
Approve
Publish
Repurpose
Review metrics
A modest content rhythm is better than a large launch followed by silence.
Source: Website Development Questions, May 7, 2026.
14
Notes: This is about sustainability. Recommend a small number of repeatable content types rather than a large editorial ambition. The process should include approval for cultural materials and a way to repurpose content into newsletter, social and print.

## Slide 15
HOW THE SYSTEM STAYS USEFUL
Measurement and governance
Current gap
The Q&A notes no active stakeholder email list and no current system for monitoring hits or source performance. That means communications reach cannot yet be measured reliably.
Recommended measurement
Website analytics, search terms, referral sources, event page visits, contact form inquiries, newsletter open/click rates and social referrals.
Recommended governance
Clear roles for content drafting, cultural review, technical updates, privacy/list management, event updates and regular reporting to leadership.
Good communications infrastructure answers two questions: who is responsible, and how do we know it is working?
Source: Website Development Questions, May 7, 2026.
15
Notes: This slide should lead to a practical discussion of responsibility. Who can approve content? Who can update the site? Who checks contact forms? Who owns the email list? Who reviews analytics monthly or quarterly?

## Slide 16
PHASED PLAN
Implementation roadmap
Phase 1
Discovery + approvals
Confirm audiences, story, visual direction, governance, content inventory and launch priorities.
Phase 2
Website build
Develop information architecture, design system, core pages, contact pathways, events/updates and analytics.
Phase 3
Tools + launch
Connect newsletter/list, social templates, print/QR materials, radio PSA copy and launch announcement.
Phase 4
Training + rhythm
Train staff, confirm editorial calendar, review analytics, refine content and maintain regular updates.
Timeline principle: “as soon as possible” still needs a sequence - approve the story and scope before building complex tools.
A three-month build can work if content, approvals and decision-making are organized early.
Source: Website Development Questions, May 7, 2026.
16
Notes: Use this as a roadmap for discussion. The actual schedule depends on the readiness of photos, written materials, approvals, logo/brand direction, and who is available for content review.

## Slide 17
MOVE FROM DISCUSSION TO ACTION
Decisions needed in the meeting
Audience priority
Which audiences must the first version of the site serve best?
Story approval
What is the approved core story and what material requires protocol review?
Visual direction
Which existing colours, logo, photos, and Village Government guidelines must guide design?
Site scope
Which pages and functions are essential for launch, and which can wait?
Content owners
Who supplies, approves and updates written material, photos and events?
Launch pathway
What public announcement, email, social, radio and print materials are needed at launch?
End the meeting with decisions, owners and next actions - not just general agreement.
Source: Website Development Questions, May 7, 2026.
17
Notes: This is your facilitation checklist. If time is limited, prioritize decisions about audience, core story, content ownership and site scope. These decisions unblock design and development.

## Slide 18
A practical next move
Build a communications platform that makes NAIC visible, understandable, contactable and actively connected to community life.
1
Confirm strategy
audiences, story, tone, approvals
2
Build the hub
website, contact pathways, content structure
3
Launch the system
email, social, print, radio, measurement
Prepared by Greenhill Communications
18
Notes: Close by returning to the main idea: the Centre already has a strong story and a clear need for visibility. The communications plan gives that story a structure, tools, workflows and a public-facing home.